## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | Estimate(hrs) | MOSCOW | Dependency | Assignee | Status
2 | 2 | US101 | Create Master Test Plan | 0.25 | MUST HAVE |  | Sumana Manna | 3-Done
2 | 2 | US102 | Prepare Product Backlog | 0.25 | MUST HAVE | US101 | Esha Kundu | 3-Done
2 | 2 | US103 | Prepare Sprint Backlog | 0.25 | MUST HAVE | US102 | Esha Kundu | 3-Done
2 | 2 | US104 | Set up environment | 0.25 | MUST HAVE |  | Sumana Manna | 3-Done
2 | 2 | US105 | Automate test cases for advanvced search of books by multiple filters | 1 | MUST HAVE | US101, US103, US104 | Esha Kundu | 3-Done
2 | 2 | US106 | Automate test cases for contact and query resolving services. | 1 | MUST HAVE | US101, US103, US104 | Sumana Manna | 3-Done
2 | 2 | US107 | Automate test cases for viewing the list for available books. | 1 | MUST HAVE | US101, US103, US104 | Jyoti | 3-Done
2 | 2 | US108 | Automate test cases for applying for a membership | 1 | MUST HAVE | US101, US103, US104 | Shreetama Das | 3-Done
2 | 2 | US109 | Execute test cases for advanvced search of books by multiple filters | 0.25 | MUST HAVE | US105 | Esha Kundu | 3-Done
2 | 2 | US110 | Execute test cases for contact and query resolving services. | 0.25 | MUST HAVE | US106 | Sumana Manna | 3-Done
2 | 2 | US111 | Execute test cases for viewing the list for available books. | 0.25 | MUST HAVE | US107 | Jyoti | 3-Done
2 | 2 | US112 | Execute test cases for applying for a membership | 0.25 | MUST HAVE | US108 | Shreetama Das | 3-Done
2 | 2 | US113 | Create Test Execution Report | 0.25 | MUST HAVE | US109, US110, US111, US112 | Esha Kundu | 3-Done
2 | 2 | US114 | Generate Extent Report | 0.5 | MUST HAVE | US109, US110, US111, US112 | Shreetama Das | 3-Done
2 | 2 | US115 | Generate Cucumber Report | 0.5 | MUST HAVE | US109, US110, US111, US112 | Shreetama Das | 3-Done