## Sheet1
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
[8 empty] | 7.25 | 0.85 | 0.25 | 1 | 0 | 1 | 1 | 3.15
SPRINT 2 BACKLOG
US101 | T001 | Create Master Test Plan | 2025-07-24 | 2025-07-30 | Sumana Manna | Design | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US102 | T002 | Prepare Product Backlog | 2025-07-24 | 2025-07-30 | Esha Kundu | Design | 3- Completed | 0.25 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0.2
US103 | T003 | Prepare Sprint Backlog | 2025-07-24 | 2025-07-30 | Esha Kundu | Design | 3- Completed | 0.25 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0.2
US104 | T004 | Set up environment | 2025-07-24 | 2025-07-24 | Sumana Manna | Build | 3- Completed | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
US105 | T005 | Automate test cases for advanvced search of books by multiple filters | 2025-07-24 | 2025-06-29 | Esha Kundu | Coding | 3- Completed | 1 | 0.25 | 0 | 0.5 | 0 | 0 | 0.25 | 0
US106 | T006 | Automate test cases for contact and query resolving services. | 2025-07-24 | 2025-07-26 | Sumana Manna | Coding | 3- Completed | 1 | 0.25 | 0.25 | 0.5 | 0 | 0 | 0 | 0
US107 | T007 | Automate test cases for viewing the list for available books. | 2025-07-28 | 2025-07-30 | Jyoti | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.25 | 0.25
US108 | T008 | Automate test cases for applying for a membership | 2025-06-28 | 2025-07-29 | Shreetama Das | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0
US109 | T009 | Execute test cases for advanvced search of books by multiple filters | 2025-07-30 | 2025-07-30 | Esha Kundu | System Test | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US110 | T010 | Execute test cases for contact and query resolving services. | 2025-07-30 | 2025-07-30 | Sumana Manna | System Test | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US111 | T011 | Execute test cases for viewing the list for available books. | 2025-07-30 | 2025-07-30 | Jyoti | System Test | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US112 | T012 | Execute test cases for applying for a membership | 2025-07-30 | 2025-07-30 | Shreetama Das | System Test | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US113 | T013 | Create Test Execution Report | 2025-07-30 | 2025-07-30 | Esha Kundu | Others | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US114 | T014 | Generate Extent Report | 2025-07-30 | 2025-07-30 | Shreetama Das | Others | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
US115 | T015 | Generate Cucumber Report | 2025-07-30 | 2025-07-30 | Shreetama Das | Others | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work